## Sheet1
Timeline for MASc. Developing Endoscopic Ear Surgery Instruments
Month: | Milestone:
2016-09-01 | Time-flow analysis of rate limiting steps in endoscopic ear surgery in operating room
Evaluation of ergonomics, strengths and weaknesses of current otologic intruments
Send out open-ended pilot questions
Assimilate responses to pilot survey and time-flow analysis to develop formal needs assessment survey
Send out survey and reminders
Solidworks course at George Brown
2017-01-01 | Assimilation and analysis of needs assessment survey
2017-02-01 | Dissemination of survey results and time-flow analysis to focus-groups and invitation to provide solutions
Feedback from on-line focus groups
2017-06-01 | Assimilation of focus-group feedback with in-house solutions and comparison with current instruments to create innovative solutions
2017-09-01 | Preparation of instruments
Testing of instruments - involve feedback from surveyed endoscopic ear surgeons
Revision of instruments
Machine Final Instruments
Testing of final instruments - time flow analysis, evaluate if instruments are improving rate-limiting steps
Survey Endoscopic Ear Surgeons for acceptance of instruments
Aug-18 | Complete write up of thesis, preparation for dissemination of results.